## Executive Summary
Social Command Center
Product Build Tracker — March 2026
~93%
Overall Completion | ~80%
Sprint 1 | Done
Sprint 2 | Done | COMPLETION | NOTES
Sprint 3 | Done | 95% | Working. Email+access code auth, middleware protection, OAuth flows for X and Reddit all solid.
PRD v1.0 | Done (Mar 9) | 100% | Full schema with 30+ models, enums, indexes. Seed file present.
tRPC Routers (47 procedures) | Mostly Done | 90% | 44/47 procedures have real DB queries. 3 stubbed: posts.publish, inbox.reply, reports.generate
Last Updated | March 9, 2026 | 95% | Full read/write adapters, hybrid routing (Official + TwitterAPI.io), token refresh, encryption.
Cron Jobs (8 workers) | Mostly Done | 90% | 7/8 fully implemented. weekly-ai-insights is stubbed (placeholder, no Claude call).
AI Pipeline (Claude) | Done | 95% | lib/ai/* all implemented: sentiment, reports, KOL scoring, content suggestions. Just not wired to all consumers.
Frontend — Dashboard | Partial | 70% | Real tRPC queries wired. Custom date range broken, mentions hardcoded to 0, no error states.
Frontend — Composer | Partial | 65% | Core create/publish wired. AI suggestions hardcoded, subreddit selector static, no mutation error handling.
Frontend — Calendar | Partial | 30% | Hardcoded to March 2026. No month nav, no real AI suggestions, padding calc wrong.
Frontend — Listening | Partial | 50% | Feed/topics wired to tRPC. AI topic generation form non-functional, sentiment charts static.
Frontend — KOL | Partial | 60% | Roster + activations wired. Discovery suggestions hardcoded, action buttons non-functional.
Frontend — Reports | Partial | 35% | List/benchmarks queries wired. Report preview completely static, export non-functional.
Frontend — Admin | Done | 85% | Well-wired. User invite/role mgmt works. Roadmap section is static. Cost tracker depends on cron activity.
Deployment (Vercel) | Done | 90% | Live at social-command-center-sand.vercel.app. Neon Postgres provisioned, all env vars configured, KV set up, crons scheduled. Auth working, accounts connected.

## Punch List
# | Priority | Area | Issue | What Needs to Happen | Effort | Blocks Deploy? | Status
1 | P0 | tRPC — posts.publish | posts.publish creates stub platformPostId instead of calling X adapter | Wire up XPlatformAdapter.publishTweet() and publishThread() with token refresh. Skip Reddit for now (no API key). | 2 hrs | Yes | Done (Sprint 1)
2 | P0 | tRPC — inbox.reply | inbox.reply only marks DB as replied, doesn't send actual reply to X | Wire up X adapter replyToTweet via XPlatformAdapter. Skip Reddit reply for now. | 1-2 hrs | Yes | Done (Sprint 1)
3 | P0 | tRPC — reports.generate | reports.generate stores placeholder content, no Claude call | Wire up lib/ai/reports.js (already implemented) to the tRPC mutation | 1 hr | Yes | Done (Sprint 1)
4 | P0 | Cron — weekly-ai-insights | Creates placeholder AIInsight with _stub: true flag | Call generateInsight() from lib/ai.js with weekly data context | 1-2 hrs | Yes | Done (Sprint 1)
5 | P0 (DONE) | Deployment — Env Vars | All env vars configured, Neon Postgres + KV provisioned, auth working, accounts connected | N/A — completed | Done | No | Done
6 | P1 | Frontend — Calendar | Hardcoded to March 2026, no month navigation, padding calc wrong | Make calendar dynamic: compute month/year, add prev/next handlers, fix startPad | 2-3 hrs | No | Done (Sprint 2)
7 | P1 | Frontend — Reports | Report preview is 100% static HTML, export buttons are no-ops | Wire report preview to reports.generate output, implement PDF/Slides export | 3-4 hrs | No | Done (Sprint 2)
8 | P1 | Frontend — Composer | AI suggestions and 'best slot' are hardcoded static text | Wire up lib/ai/content-suggestions.js to composer UI | 2-3 hrs | No | In Progress (Sprint 3)
9 | P2 (DEFERRED) | Frontend — Composer | Reddit subreddit selector only shows 3 hardcoded subreddits | Deferred — no Reddit API key. Fetch user's subscribed subreddits when Reddit is enabled. | — | No | Deferred
10 | P1 | Frontend — Dashboard | Mentions metric hardcoded to 0 (line 92) | Query actual mention count from Mention table for the date range | 30 min | No | Done (Sprint 2)
11 | P1 | Frontend — Dashboard | Custom date range option exists but has no handler | Implement date picker popover with custom range selection | 1-2 hrs | No | Not Started
12 | P1 | Frontend — Listening | AI topic generation form visible but mutation not connected | Wire form submit to listening.generateQueries tRPC mutation | 1 hr | No | Done (Sprint 2)
13 | P1 | Frontend — KOL | Discovery suggestions are hardcoded, action buttons do nothing | Wire to backend KOL search/suggest, implement add/dismiss handlers | 2-3 hrs | No | Partial (Sprint 2)
14 | P2 | Frontend — All Pages | No error boundaries or error states for failed API calls | Add React error boundaries + per-query error UI with retry buttons | 3-4 hrs | No | Done (Sprint 3)
15 | P2 | Frontend — Dashboard | Account switcher dropdown shows avatars but isn't clickable | Implement dropdown with account selection + filtered view | 1-2 hrs | No | Not Started
16 | P2 | Analytics — brandSentiment | drivers and alerts arrays hardcoded empty in tRPC router | Compute sentiment drivers from listening data, generate alert conditions | 2-3 hrs | No | Not Started
17 | P2 | Frontend — Admin | Roadmap section is static hardcoded data | Either make it dynamic (backed by DB) or remove it | 1 hr | No | Done (Sprint 3)
18 | P2 | Cron — poll-mentions | MentionType always hardcoded to MENTION, no differentiation | Classify mention type (REPLY, QUOTE, DM) based on platform API response | 1-2 hrs | No | Not Started
19 | P2 (DEFERRED) | Cron — publish-scheduled | Reddit posts fail silently if subreddit field is null | Deferred — no Reddit API key. Add validation when Reddit is enabled. | — | No | Deferred
20 | P2 | Security | encryption.js has no error handling if TOKEN_ENCRYPTION_KEY is missing | Add startup check and clear error message for missing encryption key | 30 min | No | Not Started
21 | P2 | Admin — apiCosts | prisma.aPICallLog may have casing issue with Prisma client | Verify Prisma generates correct model accessor name, fix if needed | 30 min | No | Not Started
22 | P1 | Testing | No test coverage for any module | Vitest + 75 unit tests (encryption, sentiment, cron-auth, classifier, env) | 3 hrs | No | Done (Sprint 4)
23 | P1 | Composer — AI | AI suggestions are hardcoded static text | New AI tRPC router + live optimize button with apply/dismiss | 2 hrs | No | Done (Sprint 4)
24 | P1 | Cron — mentions | All mentions classified as MENTION (no REPLY/QUOTE/DM) | mention-classifier.js utility + wired into poll-mentions cron | 1.5 hrs | No | Done (Sprint 4)
25 | P2 | Security | No validation of TOKEN_ENCRYPTION_KEY at startup | validate-env.js — checks all required vars + key format | 1 hr | No | Done (Sprint 4)

## Feature Map
Feature | Schema | tRPC Router | Cron Job | AI Module | Frontend Page | Overall
Auth (email + access code) | Done | N/A | N/A | N/A | Done | Done
OAuth — X (PKCE) | Done | N/A | N/A | N/A | Done | Done
OAuth — Reddit | Done | N/A | N/A | N/A | Done | Done
Token Refresh | Done | N/A | Used by crons | N/A | N/A | Done
Encryption at rest | Done | N/A | N/A | N/A | N/A | Done
Account management | Done | Done (2 procs) | N/A | N/A | Done | Done
Post creation (draft) | Done | Done | N/A | N/A | Done | Done
Post scheduling | Done | Done | publish-scheduled | N/A | Done | Done
Post publishing | Done | Stubbed | Done | N/A | Partial | Stubbed
Thread publishing | Done | Stubbed | Done | N/A | Partial | Stubbed
Inbox — list/read/archive | Done | Done | poll-mentions | N/A | Partial | Partial
Inbox — reply to platform | Done | Stubbed | N/A | N/A | Partial | Stubbed
Social listening — topics | Done | Done (9 procs) | poll-listening | N/A | Partial | Partial
Social listening — AI queries | Done | Done | N/A | Done | Partial | Partial
Sentiment analysis | Done | N/A | Used in scanner | Done (keyword + Claude) | Static | Partial
Analytics dashboard | Done | Done (8 procs) | daily-analytics | N/A | Partial | Partial
Analytics — backfill history | Done | Done | backfill-history | N/A | Done | Done
Competitor tracking | Done | Done (4 procs) | N/A | N/A | Partial | Partial
KOL tracking | Done | Done (5 procs) | kol-activations | Done (scoring) | Partial | Partial
AI reports | Done | Stubbed | N/A | Done | Static | Stubbed
AI weekly insights | Done | N/A | Stubbed | Done | N/A | Stubbed
AI content suggestions | N/A | N/A | N/A | Done | Static | Partial
User management | Done | Done | N/A | N/A | Done | Done
API cost tracking | Done | Done | Logged in all crons | N/A | Done | Done
Audit logging | Done | Done | Logged in crons | N/A | Partial | Partial
Alert rules | Done | N/A | Checked in crons | N/A | Not Started | Partial
Calendar view | Done | Done (via posts.list) | N/A | N/A | Partial | Partial
Report export (PDF/Slides) | N/A | N/A | N/A | N/A | Not Started | Not Started

## Roadmap
Recommended Build Sequence
Work in this order to unblock deploy fastest
Sprint 1 (Done) | Focus | Tasks | Est. Hours | Outcome
Sprint 2 (Done) | Wire the 4 Stubs (X only) | 1. Calendar: dynamic month navigation, Mon-start weeks, correct padding 2. Dashboard: wired real mentions count from DB 3. Composer: fixed mutation field names (accountId, contentType) 4. Reports: added type selector, dynamic AI-powered renderer 5. Listening: conversational AI query generation with clarifying questions 6. Analytics router: added mentionCount to dashboard response | 5-7 hrs | All 7 pages show real data. AI reports render dynamically. Listening has conversational flow. 8 files changed, +507/-156 lines.
Sprint 3 (Done) | Hardening & DX | 1. ErrorBoundary + ToastProvider in components/ui.jsx 2. Production README with architecture, env vars, setup instructions 3. Cron monitoring utility (lib/cron-monitor.js) with Slack alerting 4. Adapter barrel exports (lib/adapters/index.js) 5. Roadmap updated in admin page to reflect actual build status 6. PRD v1.0 document (10 sections, 28 roadmap items) 7. Build tracker updated | 4-6 hrs | Production-quality DX. Error handling system. Cron observability. Proper documentation. PRD v1.0 complete.
Sprint 4 (In Progress) | Testing & Quality | 1. Vitest test framework + 75 unit tests across 5 suites (encryption, sentiment, cron-auth, mention-classifier, env-validation) 2. AI router (ai.optimizeThread, ai.predictPerformance, ai.suggestContent) 3. Composer AI wiring — live optimize button + apply suggestions 4. Mention type classifier (REPLY, QUOTE, DM) wired into poll-mentions cron 5. Environment validation module (validate-env.js) with production fail-fast 6. Admin roadmap updated to 28 items across 4 phases | 8-10 hrs | 75 passing tests. AI-powered composer. Smart mention classification. Env safety net. 11 files added/modified.
Sprint 5 (Next) | Scale & Extend | 1. Playwright E2E tests for core user flows 2. Individual auth (SSO/email login replacing team password) 3. Image/media upload in posts 4. Account switcher dropdown in composer 5. Notification system (Slack/email from AlertRule model) 6. Reddit integration (when API key available) 7. Mobile-responsive layout | 12-16 hrs | Full-featured v2. Individual accountability. Multi-platform support.